## Programme
10 New Burlington Street
15 Oct 2026–21 Jun 2027 · Provisional programme
Programme overview | Controllers | Floors | Programme notes and conditions ↗ | [167 empty] | Programme notes and conditions ↗
Day view · Click outline 1 for weeks · 2 for days · + or − opens or closes one week
● Validation ● Design ● Software ● Graphics ● Installation ● Commissioning ● Witness / handover
Work package | Start | Finish | Oct 2026 | [23 empty] | Nov 2026 | [39 empty] | Dec 2026 | [31 empty] | Jan 2027 | [31 empty] | Feb 2027 | [31 empty] | Mar 2027 | [31 empty] | Mar 2027 | [7 empty] | Apr 2027 | [31 empty] | May 2027 | [39 empty] | Jun 2027 | [15 empty] | Jun 2027
 | time axis 2026-10-12 to 2027-06-27
|  |  | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2027 | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Programme | 2026-10-15 08:00 | 2027-06-21 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Approvals, procurement and access | 2026-10-15 08:00 | 2026-11-02 10:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Upfront validation | 2026-10-29 08:00 | 2026-11-30 16:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Survey and technical validation | 2026-10-29 08:00 | 2026-11-30 16:00
Validation findings reviewed | 2026-11-30 16:00 | 2026-11-30 16:00
[59 empty] | ◆ | ◆
Project engineering | 2026-10-15 08:00 | 2027-01-29 16:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Design | 2026-10-15 08:00 | 2026-11-09 16:00
Software | 2026-11-09 08:00 | 2027-01-22 16:00
Graphics | 2026-11-16 08:00 | 2027-01-29 16:00
MCC 1 | 2026-12-07 08:00 | 2026-12-15 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2026-12-07 08:00 | 2026-12-11 16:00
Functional commissioning | 2026-12-14 08:00 | 2026-12-14 16:00
Witness / handover | 2026-12-15 08:00 | 2026-12-15 14:00
MCC 2 | 2026-12-14 08:00 | 2026-12-22 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2026-12-14 08:00 | 2026-12-18 16:00
Functional commissioning | 2026-12-21 08:00 | 2026-12-21 16:00
Witness / handover | 2026-12-22 08:00 | 2026-12-22 14:00
MCC 3 | 2026-10-15 12:00 | 2027-01-12 12:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Controller identification and scope review | 2026-10-15 12:00 | 2026-10-15 14:00
Installation / changeover | 2027-01-04 08:00 | 2027-01-08 16:00
Functional commissioning | 2027-01-11 08:00 | 2027-01-11 16:00
Witness / handover | 2027-01-12 08:00 | 2027-01-12 12:00
MCC 4 | 2027-01-11 08:00 | 2027-01-21 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-01-11 08:00 | 2027-01-15 16:00
Functional commissioning | 2027-01-18 08:00 | 2027-01-20 16:00
Witness / handover | 2027-01-21 08:00 | 2027-01-21 14:00
MCC 5 | 2027-01-18 08:00 | 2027-01-28 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-01-18 08:00 | 2027-01-22 16:00
Functional commissioning | 2027-01-25 08:00 | 2027-01-27 16:00
Witness / handover | 2027-01-28 08:00 | 2027-01-28 14:00
MCC 6 | 2026-10-15 14:00 | 2027-02-08 12:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Controller identification and scope review | 2026-10-15 14:00 | 2026-10-15 16:00
Installation / changeover | 2027-01-29 08:00 | 2027-02-04 16:00
Functional commissioning | 2027-02-05 08:00 | 2027-02-05 16:00
Witness / handover | 2027-02-08 08:00 | 2027-02-08 12:00
MCC 7 | 2027-02-05 08:00 | 2027-02-15 15:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-02-05 08:00 | 2027-02-11 16:00
Functional commissioning | 2027-02-12 08:00 | 2027-02-15 09:00
Witness / handover | 2027-02-15 09:00 | 2027-02-15 15:00
MCC 8 | 2027-02-12 08:00 | 2027-02-24 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-02-12 08:00 | 2027-02-18 16:00
Functional commissioning | 2027-02-19 08:00 | 2027-02-23 16:00
Witness / handover | 2027-02-24 08:00 | 2027-02-24 14:00
MCC 9 | 2027-02-19 08:00 | 2027-03-02 09:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-02-19 08:00 | 2027-02-25 16:00
Functional commissioning | 2027-02-26 08:00 | 2027-03-01 11:30
Witness / handover | 2027-03-01 11:30 | 2027-03-02 09:30
MCC 10 | 2027-02-26 08:00 | 2027-03-09 10:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-02-26 08:00 | 2027-03-04 16:00
Functional commissioning | 2027-03-05 08:00 | 2027-03-08 12:30
Witness / handover | 2027-03-08 12:30 | 2027-03-09 10:30
Ground floor | 2027-03-13 08:00 | 2027-03-26 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Terminal controls — installation | 2027-03-13 08:00 | 2027-03-13 16:00
Terminal controls — standalone commissioning | 2027-03-20 08:00 | 2027-03-20 16:00
Riser upgrades — installation | 2027-03-22 17:00 | 2027-03-23 21:00
Riser upgrades — commissioning | 2027-03-24 17:00 | 2027-03-25 21:00
Integration holdpoint | 2027-03-26 08:00 | 2027-03-26 08:00
[187 empty] | ◆ |  |  |  |  | ◆
Progressive witness / handover | 2027-03-26 08:00 | 2027-03-26 14:00
Level 1 | 2027-03-14 08:00 | 2027-04-05 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Standard FCU zones — installation | 2027-03-14 08:00 | 2027-03-14 16:00
Standard FCU zones — standalone commissioning | 2027-03-20 08:00 | 2027-03-20 16:00
Panel changeovers | 2027-03-24 17:00 | 2027-03-25 21:00
Functional commissioning | 2027-03-25 08:00 | 2027-03-29 12:00
Riser upgrades — installation | 2027-03-26 17:00 | 2027-03-31 21:00
Riser upgrades — commissioning | 2027-03-30 17:00 | 2027-04-02 21:00
Integration holdpoint | 2027-04-05 08:00 | 2027-04-05 08:00
[203 empty] | ◆ | ◆
Progressive witness / handover | 2027-03-26 08:00 | 2027-04-05 14:00
Level 2 | 2027-03-20 08:00 | 2027-04-15 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Standard FCU zones — installation · 2 phased batches | 2027-03-20 08:00 | 2027-03-27 16:00
Standard FCU zones — standalone commissioning · 2 phased batches | 2027-03-27 08:00 | 2027-04-03 16:00
Panel changeovers | 2027-04-05 17:00 | 2027-04-06 21:00
Functional commissioning | 2027-04-06 08:00 | 2027-04-07 16:00
Riser upgrades — installation | 2027-04-07 17:00 | 2027-04-12 21:00
Riser upgrades — commissioning | 2027-04-09 17:00 | 2027-04-14 21:00
Integration holdpoint | 2027-04-15 08:00 | 2027-04-15 08:00
[211 empty] | ◆ |  |  |  | ◆
Progressive witness / handover | 2027-04-07 08:00 | 2027-04-15 14:00
Level 3 · scope to agree | 2027-04-03 08:00 | 2027-04-27 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Standard FCU zones — installation · 2 phased batches | 2027-04-03 08:00 | 2027-04-10 16:00
Standard FCU zones — standalone commissioning · 2 phased batches | 2027-04-10 08:00 | 2027-04-17 16:00
Ornate / same-weekend zones — installation | 2027-04-17 08:00 | 2027-04-17 16:00
Ornate / same-weekend zones — standalone commissioning | 2027-04-18 08:00 | 2027-04-18 16:00
Riser upgrades — installation | 2027-04-19 17:00 | 2027-04-22 21:00
Riser upgrades — commissioning | 2027-04-21 17:00 | 2027-04-26 21:00
Integration holdpoint | 2027-04-27 08:00 | 2027-04-27 08:00
[227 empty] | ◆ |  | ◆
Progressive witness / handover | 2027-04-27 08:00 | 2027-04-27 14:00
Level 4 | 2027-04-24 08:00 | 2027-05-24 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Standard FCU zones — installation · 2 phased batches | 2027-04-24 08:00 | 2027-05-02 16:00
Standard FCU zones — standalone commissioning · 2 phased batches | 2027-05-01 08:00 | 2027-05-09 16:00
Panel changeovers | 2027-05-10 17:00 | 2027-05-13 21:00
Functional commissioning | 2027-05-11 08:00 | 2027-05-17 09:00
Riser upgrades — installation | 2027-05-14 17:00 | 2027-05-19 21:00
Riser upgrades — commissioning | 2027-05-18 17:00 | 2027-05-21 21:00
Integration holdpoint | 2027-05-24 08:00 | 2027-05-24 08:00
[259 empty] | ◆ | ◆
Progressive witness / handover | 2027-05-12 08:00 | 2027-05-24 14:00
Level 5 | 2027-05-08 08:00 | 2027-06-03 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Standard FCU zones — installation · 2 phased batches | 2027-05-08 08:00 | 2027-05-16 16:00
Standard FCU zones — standalone commissioning · 2 phased batches | 2027-05-15 08:00 | 2027-05-23 16:00
Panel changeovers | 2027-05-24 17:00 | 2027-05-25 21:00
Functional commissioning | 2027-05-25 08:00 | 2027-05-26 16:00
Riser upgrades — installation | 2027-05-26 17:00 | 2027-05-31 21:00
Riser upgrades — commissioning | 2027-05-28 17:00 | 2027-06-02 21:00
Integration holdpoint | 2027-06-03 08:00 | 2027-06-03 08:00
[267 empty] | ◆ |  |  |  | ◆
Progressive witness / handover | 2027-05-26 08:00 | 2027-06-03 14:00
Level 6 | 2027-05-22 08:00 | 2027-06-17 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Terminal controls — installation · 2 phased batches | 2027-05-22 08:00 | 2027-05-30 16:00
Terminal controls — standalone commissioning · 2 phased batches | 2027-05-29 08:00 | 2027-06-06 16:00
Ornate / same-weekend zones — installation | 2027-06-05 08:00 | 2027-06-05 16:00
Ornate / same-weekend zones — standalone commissioning | 2027-06-06 08:00 | 2027-06-06 16:00
Panel changeovers | 2027-06-07 17:00 | 2027-06-08 21:00
Functional commissioning | 2027-06-08 08:00 | 2027-06-09 16:00
Riser upgrades — installation | 2027-06-09 17:00 | 2027-06-14 21:00
Riser upgrades — commissioning | 2027-06-11 17:00 | 2027-06-16 21:00
Integration holdpoint | 2027-06-17 08:00 | 2027-06-17 08:00
[283 empty] | ◆ |  |  |  | ◆
Progressive witness / handover | 2027-06-09 08:00 | 2027-06-17 14:00
Interfaces and central controls | 2027-01-25 08:00 | 2027-06-15 11:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Installation / changeover | 2027-01-25 08:00 | 2027-06-08 16:00
Functional commissioning | 2027-02-01 08:00 | 2027-06-14 13:30
Witness / handover | 2027-02-02 08:00 | 2027-06-15 11:30
Integrated testing and handover | 2027-06-17 14:00 | 2027-06-21 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11; 2026-12-14 to 2026-12-18; 2026-12-21 to 2026-12-25; 2026-12-28 to 2027-01-01; 2027-01-04 to 2027-01-08; 2027-01-11 to 2027-01-15; 2027-01-18 to 2027-01-22; 2027-01-25 to 2027-01-29; 2027-02-01 to 2027-02-05; 2027-02-08 to 2027-02-12; 2027-02-15 to 2027-02-19; 2027-02-22 to 2027-02-26; 2027-03-01 to 2027-03-05; 2027-03-08 to 2027-03-12; 2027-03-15 to 2027-03-19; 2027-03-22 to 2027-03-26; 2027-03-29 to 2027-04-02; 2027-04-05 to 2027-04-09; 2027-04-12 to 2027-04-16; 2027-04-19 to 2027-04-23; 2027-04-26 to 2027-04-30; 2027-05-03 to 2027-05-07; 2027-05-10 to 2027-05-14; 2027-05-17 to 2027-05-21; 2027-05-24 to 2027-05-28; 2027-05-31 to 2027-06-04; 2027-06-07 to 2027-06-11; 2027-06-14 to 2027-06-18; 2027-06-21 to 2027-06-25
Programme notes and conditions
Provisional planning dates: scope, access and software release targets remain subject to agreement.
The survey and technical validation period is provisional, with labour and resources unestimated. Findings require review before physical upgrades; the calendar allocation does not establish readiness or approval.
One installation team of two people; one panel at a time. Main MCC works precede floor works.
Commissioning allowance: 2 engineers.
Large standard zones are phased into batches of up to 40 controls. Each batch installs on one weekend and commissions the next; later-batch installation may overlap earlier-batch commissioning. Physical batch boundaries and productivity remain provisional.
MCC installations use provisional package release dates within the overall engineering periods. These dates require review and do not represent completed engineering or accepted software releases.
Engineering resources: 1 designer, 1 software engineer, 1 graphics engineer.
Engineering dates are shown as planned periods: continuous calendar blocks including weekends and the assumed closure. They are allocations, not labour bookings or a resource-levelled workload forecast; they do not establish that the full engineering workload fits the listed resources.
Design period: 15 Oct 2026–09 Nov 2026.
Software period: 09 Nov 2026–22 Jan 2027.
Graphics period: 16 Nov 2026–29 Jan 2027.
The forecast covers the estimated work. Remaining shared software implementation, validation and release is not fully estimated; a complete project finish is not established by these dates.
Assumed planning closure: 24 Dec 2026–03 Jan 2027 inclusive. Other access and recovery restrictions remain to be agreed.
Standard linked works install one weekend and commission the following weekend.
Designated special / ornate zones install and commission within the same weekend.
FCU installation and standalone commissioning precede each floor’s panel changeovers and dedicated riser upgrades. Final floor witnessing and handover follow integration; panel witnessing and handover are progressive.
Durations and productivity include provisional allowances. Confirmed progress and approvals are recorded separately in the planning application.