## Programme
Citadel Leak Detection
Weekend works: 31 October–22 November 2026 · Provisional programme
Programme overview |  |  | Programme notes and conditions ↗
Day view · Click outline 1 for weeks · 2 for days · + or − opens or closes one week
● Design ● Software ● Graphics ● Installation ● Commissioning ● Witness / handover
Work package | Start | Finish | Oct 2026 | [23 empty] | Nov 2026
 | time axis 2026-10-12 to 2026-11-22
|  |  | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Project programme | 2026-10-15 08:00 | 2026-11-22 15:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
◆
Design, software and graphics | 2026-10-15 08:00 | 2026-10-23 17:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Design | 2026-10-15 08:00 | 2026-10-20 17:00
Software | 2026-10-21 08:00 | 2026-10-23 17:00
Graphics and alarm routing | 2026-10-21 08:00 | 2026-10-22 17:00
Design, software and graphics issued | 2026-10-23 17:00 | 2026-10-23 17:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
[11 empty] | ◆ |  |  |  |  | ◆
Access, deliveries and scope release for Weekend 1 | 2026-10-30 17:00 | 2026-10-30 17:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
[19 empty] | ◆ |  |  |  |  | ◆
L5 switch room 05 N13 | 2026-10-31 08:00 | 2026-11-08 11:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-10-31 08:00 | 2026-10-31 17:00
Functional commissioning | 2026-11-01 08:00 | 2026-11-08 11:30
Alarms proven and location returned to service | 2026-11-08 11:30 | 2026-11-08 11:30
[27 empty] | ◆ | [6 empty] | ◆
L5 kitchen 05 N09 | 2026-11-14 13:00 | 2026-11-21 14:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-14 13:00 | 2026-11-15 12:00
Functional commissioning | 2026-11-15 16:30 | 2026-11-21 14:00
Alarms proven and location returned to service | 2026-11-21 14:00 | 2026-11-21 14:00
[43 empty] | ◆ | [5 empty] | ◆
L8 switch room | 2026-11-01 08:00 | 2026-11-21 10:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-01 08:00 | 2026-11-14 12:00
Functional commissioning | 2026-11-15 08:00 | 2026-11-21 10:00
Alarms proven and location returned to service | 2026-11-21 10:00 | 2026-11-21 10:00
[43 empty] | ◆ | [5 empty] | ◆
L14 tea / snack cupboard | 2026-10-31 08:00 | 2026-11-21 15:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-10-31 08:00 | 2026-11-15 12:00
Functional commissioning | 2026-11-21 10:00 | 2026-11-21 15:30
Alarms proven and location returned to service | 2026-11-21 15:30 | 2026-11-21 15:30
[43 empty] | ◆ | [5 empty] | ◆
L14 shower / cleaners | 2026-11-14 08:00 | 2026-11-21 14:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-14 08:00 | 2026-11-14 17:00
Functional commissioning | 2026-11-15 13:00 | 2026-11-21 14:30
Alarms proven and location returned to service | 2026-11-21 14:30 | 2026-11-21 14:30
[43 empty] | ◆ | [5 empty] | ◆
L14 new IDF Andel panel | 2026-10-31 13:00 | 2026-11-08 16:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-10-31 13:00 | 2026-11-01 17:00
Functional commissioning | 2026-11-07 08:00 | 2026-11-08 11:30
Witness / handover | 2026-11-08 11:30 | 2026-11-08 16:30
L15 north tank / toilet tank | 2026-10-31 13:00 | 2026-11-08 17:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-10-31 13:00 | 2026-11-07 12:00
Functional commissioning | 2026-11-07 13:00 | 2026-11-08 17:00
Alarms proven and location returned to service | 2026-11-08 17:00 | 2026-11-08 17:00
[27 empty] | ◆ | [6 empty] | ◆
L15 shower / all-gender WC | 2026-11-01 13:00 | 2026-11-08 17:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-01 13:00 | 2026-11-07 12:00
Functional commissioning | 2026-11-07 13:00 | 2026-11-08 17:00
Alarms proven and location returned to service | 2026-11-08 17:00 | 2026-11-08 17:00
[27 empty] | ◆ | [6 empty] | ◆
L15 IDF (scope to confirm) | 2026-11-07 08:00 | 2026-11-14 16:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-07 08:00 | 2026-11-07 17:00
Functional commissioning | 2026-11-08 11:30 | 2026-11-14 16:30
Alarms proven and location returned to service | 2026-11-14 16:30 | 2026-11-14 16:30
[35 empty] | ◆ | [5 empty] | ◆
L16 post room 16N 112 | 2026-11-01 08:00 | 2026-11-15 11:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-01 08:00 | 2026-11-08 12:00
Functional commissioning | 2026-11-08 16:30 | 2026-11-15 11:30
Alarms proven and location returned to service | 2026-11-15 11:30 | 2026-11-15 11:30
[35 empty] | ◆ | [6 empty] | ◆
L16 male changing room | 2026-11-07 13:00 | 2026-11-15 12:00 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-07 13:00 | 2026-11-08 12:00
Functional commissioning | 2026-11-14 08:00 | 2026-11-15 12:00
Alarms proven and location returned to service | 2026-11-15 12:00 | 2026-11-15 12:00
[35 empty] | ◆ | [6 empty] | ◆
L16 IDF (scope to confirm) | 2026-11-08 08:00 | 2026-11-15 16:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-08 08:00 | 2026-11-08 17:00
Functional commissioning | 2026-11-14 08:00 | 2026-11-15 16:30
Alarms proven and location returned to service | 2026-11-15 16:30 | 2026-11-15 16:30
[35 empty] | ◆ | [6 empty] | ◆
L15 security 15S 314 (scope to confirm) | 2026-11-08 13:00 | 2026-11-21 11:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Installation / changeover | 2026-11-08 13:00 | 2026-11-14 12:00
Functional commissioning | 2026-11-14 16:30 | 2026-11-21 11:30
Alarms proven and location returned to service | 2026-11-21 11:30 | 2026-11-21 11:30
[43 empty] | ◆ | [5 empty] | ◆
Integrated testing and handover | 2026-11-21 15:30 | 2026-11-22 15:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
Integrated alarm review and final reinstatement | 2026-11-21 15:30 | 2026-11-22 10:30
Client witness, defects and operating handover | 2026-11-22 10:30 | 2026-11-22 15:30
Completion and handover | 2026-11-22 15:30 | 2026-11-22 15:30 | bar: 2026-10-12 to 2026-10-16; 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20
[43 empty] | ◆ | [6 empty] | ◆
Programme notes and conditions
Site works: 31 October–1 November, 7–8 November, 14–15 November and 21–22 November 2026.
Design, software and graphics package for issue on 23 October 2026, before the first working weekend.
Programme includes 13 leak detection locations. Scope, point counts and ALC connections for L15 IDF, L16 IDF and security room 15S 314 require confirmation.
Working hours: 08:00–12:00 and 13:00–17:00 each Saturday and Sunday, subject to agreed access and permits.
Planned resources: three installation teams of two electricians, up to four ALC commissioning engineers, up to two landlord BMS engineers and one leak detection specialist team. Attendance and client witnessing to be agreed.
Site commencement is subject to material delivery, panel manufacture, agreed scope and variations, and specialist availability. Expedited delivery for 31 October requires confirmation.
Cabling and ALC panel preparation proceed in parallel. Installation release precedes commissioning and tenant/landlord alarm tests. Existing landlord alarm services must be maintained throughout the works, with agreed monitoring and rollback arrangements.
Final integration, client witnessing and handover follow completion of all location tests. Completion on 22 November is subject to the stated scope, deliveries, access, attendance and satisfactory testing. Changes or failed tests may require an additional visit.