## Programme
Leonardo Luton Phase 3
FCU works: 20 October-9 December 2026 · REVISION 3 - FOR REVIEW
Programme overview |  |  | Programme notes and conditions ↗
Day view · Click outline 1 for weeks · 2 for days · + or − opens or closes one week
● Installation ● Commissioning ● Witness / handover ● Buffer / reserved time
Work package | Start | Finish | Oct 2026 | [15 empty] | Nov 2026 | [39 empty] | Dec 2026
 | time axis 2026-10-19 to 2026-12-13
|  |  | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun | 2026 | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Access and shutdown confirmations | 2026-10-19 16:00 | 2026-11-06 16:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
|  |  | ◆ | ◆ | [14 empty] | ◆ |  |  |  |  | ◆
FCU access and scope review due | 2026-10-19 16:00 | 2026-10-19 16:00
|  |  | ◆ | ◆
Shutdown readiness review due | 2026-11-06 16:00 | 2026-11-06 16:00
[19 empty] | ◆ |  |  |  |  | ◆
FCU networks - first fix | 2026-10-20 08:00 | 2026-11-06 16:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
B Level 1 - first fix complete | — | — | 2026-10-19: Reported complete
A Level 3 North - first fix | 2026-10-20 08:00 | 2026-10-20 16:00
A Level 3 South - first fix | 2026-10-21 08:00 | 2026-10-21 16:00
A Level 3 - shared floor buffer | 2026-10-22 08:00 | 2026-10-22 16:00
A Level 2 North - first fix | 2026-10-28 08:00 | 2026-10-28 16:00
A Level 2 South - first fix | 2026-10-29 08:00 | 2026-10-29 16:00
A Level 2 - shared floor buffer | 2026-10-30 08:00 | 2026-10-30 16:00
A Level 1 North - first fix | 2026-11-02 08:00 | 2026-11-02 16:00
A Level 1 South - first fix | 2026-11-03 08:00 | 2026-11-03 16:00
A Level 1 - shared floor buffer | 2026-11-04 08:00 | 2026-11-04 16:00
A Ground North - first fix | 2026-11-05 08:00 | 2026-11-05 16:00
A Ground North - shared floor buffer | 2026-11-06 08:00 | 2026-11-06 16:00
Fibre and Building B AHU wiring | 2026-10-23 20:00 | 2026-10-27 16:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
MCC02 to MCC01 - fibre cable run, one night | 2026-10-23 20:00 | 2026-10-24 04:00
Building B AHU 1-4 - humidity sensor wiring | 2026-10-26 08:00 | 2026-10-27 16:00
Shutdown weekend - 7 and 8 November | 2026-11-07 08:00 | 2026-11-08 16:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
Heater batteries and humidity - install and safety tests | 2026-11-07 08:00 | 2026-11-08 16:00
Fibre splicing, terminations and link tests | 2026-11-07 08:00 | 2026-11-08 16:00
Plant return-to-service review due | 2026-11-08 16:00 | 2026-11-08 16:00
[19 empty] | ◆ | [6 empty] | ◆
FCU networks - second fix | 2026-11-17 20:00 | 2026-11-27 04:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
A Level 3 North - second fix, one night | 2026-11-17 20:00 | 2026-11-18 04:00
A Level 3 South - second fix, one night | 2026-11-18 20:00 | 2026-11-19 04:00
A Level 2 North - second fix, one night | 2026-11-19 20:00 | 2026-11-20 04:00
A Level 2 South - second fix, one night | 2026-11-20 20:00 | 2026-11-21 04:00
A Level 1 North - second fix, one night | 2026-11-23 20:00 | 2026-11-24 04:00
A Level 1 South - second fix, one night | 2026-11-24 20:00 | 2026-11-25 04:00
A Ground North - second fix, one night | 2026-11-25 20:00 | 2026-11-26 04:00
B Level 1 offices - second fix, one night | 2026-11-26 20:00 | 2026-11-27 04:00
FCU commissioning, software and graphics | 2026-11-30 08:00 | 2026-12-09 16:00 | bar: 2026-10-19 to 2026-10-23; 2026-10-26 to 2026-10-30; 2026-11-02 to 2026-11-06; 2026-11-09 to 2026-11-13; 2026-11-16 to 2026-11-20; 2026-11-23 to 2026-11-27; 2026-11-30 to 2026-12-04; 2026-12-07 to 2026-12-11
A Level 3 North - commission, software and graphics | 2026-11-30 08:00 | 2026-11-30 16:00
A Level 3 South - commission, software and graphics | 2026-12-01 08:00 | 2026-12-01 16:00
A Level 2 North - commission, software and graphics | 2026-12-02 08:00 | 2026-12-02 16:00
A Level 2 South - commission, software and graphics | 2026-12-03 08:00 | 2026-12-03 16:00
A Level 1 North - commission, software and graphics | 2026-12-04 08:00 | 2026-12-04 16:00
A Level 1 South - commission, software and graphics | 2026-12-07 08:00 | 2026-12-07 16:00
A Ground North - commission, software and graphics | 2026-12-08 08:00 | 2026-12-08 16:00
B Level 1 offices - commission, software and graphics | 2026-12-09 08:00 | 2026-12-09 16:00
FCU works review due | 2026-12-09 16:00 | 2026-12-09 16:00
[59 empty] | ◆ |  |  | ◆
Remaining Phase 3 scope - dates to agree | — | — | 2026-10-19: Dates to agree
Detailed design, survey and criticality | — | — | 2026-10-19: Dates to agree
BMS data quality and historian | — | — | 2026-10-19: Dates to agree
Simmtronic occupancy integration | — | — | 2026-10-19: Dates to agree
IAQ, ToF and LoRaWAN installation/integration | — | — | 2026-10-19: Dates to agree
Thermal-core occupancy and IAQ controls | — | — | 2026-10-19: Dates to agree
Chilled water and AHU dehumidification | — | — | 2026-10-19: Dates to agree
Energy meters and submetering | — | — | 2026-10-19: Dates to agree
FDD, energy and carbon dashboards; alarms | — | — | 2026-10-19: Dates to agree
ISS command wall | — | — | 2026-10-19: Dates to agree
Integrated proving, training and handover | — | — | 2026-10-19: Dates to agree
Post-installation stability and seasonal review | — | — | 2026-10-19: Dates to agree
Lab 5 airflow and filter follow-up | — | — | 2026-10-19: Dates to agree
Programme notes and conditions
First fix: one day per core. Levels 3, 2 and 1 each allow one day North, one day South and one shared buffer day for the whole floor. Buffer days allow for unforeseen work. Ground North allows one workday and one provisional buffer day; Ground South is excluded.
Building B first fix is complete. Building B second fix and commissioning remain in the programme, subject to scope confirmation. One controls crew is allocated throughout the FCU sequence.
Fibre cabling is scheduled after Level 3 on 23 October night to support splicing on 7-8 November. The sequence, route, permits and IT configuration require confirmation. Building B AHU 1-4 humidity wiring is scheduled for 26-27 October.
Day shifts allow 08:00-16:00. Night shifts allow 20:00-04:00 and are dated by the starting evening. A night crosses two calendar dates but represents one shift. No day shift follows a night shift. Monday 9 November is reserved for recovery after the shutdown weekend. Exact access hours remain to agree.
The 7-8 November shutdown is subject to equipment, permits, isolations and specialist availability. Heater duties, electrical capacity and the Lab 5 airflow/filter findings require review. Prove the safety interlocks before plant return. Mechanical/electrical support and fibre specialists are additional resources to confirm.
Second fix returns on 17 November, four weeks from the initial start. The programme retains one night per listed core or area, followed by one combined day for commissioning, software and graphics. First-fix allocations, including buffers, finish on 6 November; the dated FCU works finish on 9 December.
Further smart-building, sensor, FDD and integrated handover activities are listed with dates to agree. Ground North routes, quantities and controller mapping require confirmation before work.